## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | JB, 3/1/2020 | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | JB, 3/1/2020 | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | JB, 3/1/2020 | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | JB, 3/1/2020 | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | JB, 3/1/2020 | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | JB, 3/1/2020 | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | JB, 3/1/2020 | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | JB, 3/1/2020 | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | JB, 3/1/2020 | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | JB, 3/1/2020. Initial Failure, would attempt to send to game route and crash server. JB, 3/1/2020. Passed fixed bug | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | JB, 3/1/2020 | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | JB, 3/1/2020 | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | JB, 3/1/2020 | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | JB, 3/1/2020 | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | JB, 3/1/2020 | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
As a Player, I want to sign-out so that I can leave the site after I’ve finished playing. | Given a player is signed in and not in a game when the Player clicks sign out then the Player should be signed out and taken to the Home Page. |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
As a Player, I want to be able to move to a diagonal spot so that I can progress the a turn | Given that it is my turn and a valid move is able to be made when I make that move then I expect my piece to be moved to that space |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
As a Player I want to be able to end a game prematurely so that I can leave the game. | Given I am playing a checkers game when I click the resign button then I expect the game to end, and I am shown the game result message |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given I am playing a checkers game when the opponent resigns then I expect to be notified and displayed the congratulations game result message |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
As a Player I want to be able to move the checkers on the board diagonally to a desired location so that the game can progress a turn. | Given that it is my turn and a valid move is able to be made when I make that move then I expect my piece to be moved to that space |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given that its my turn when I have a jump move able to be made, then I must make that jump move |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given that its my turn when I have multiple jump moves able to be made, then I must choose one of the jump move to be made |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given that it's my turn and a jump move is able to be made when I make that jump move then I expect the opponents piece to be eradicated and for my piece to be placed in the spot diagonally across from it's current position |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given I have jumped over an opponent's piece, when there are multiple jump moves able to be made, then I have the choice of which jump move to make. |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given I have jumped over an opponent's piece, when there is a jump move able to be made, then I must make that jump move. |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
As a Player I want my piece to become king when I reach the king row so that the game rules are followed. | Given player is in a game of checkers when a checker reaches the other side of the board then the checker will be crowned king. |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given a player has a king piece, when the player moves the king piece, allow for moves in forward and backward diagonal directions. |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given that it is my turn, when I have a king piece, then I expect that king piece to be able to move or jump in any diagonal direction. |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
As a Player I want to be able to win so that I know I won the game. | Given that I am in a game when I capture all my opponent's pieces, then I should win and be taken to the congratulations result page. |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given that I am in a game when I leave my opponent no options for moving, then I should win and be taken to the congratulations result page. |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given that I am in a game when my opponent clicks resign, then I should be taken to the congratulations result page. |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
As a player, I want to see a congratulations message when I win so that I can feel accomplished. | Given I am playing checkers when I win the game then I expect to be shown a congratulations message |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given I am playing checkers when I lose the game then I expect to be shown a "you lose" message |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given I am seeing a game result message when I click the exit button then I expect to be redirected back to home. |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
| Given I am seeing a game result message when I wait for longer than some amount of time then I expect to automatically be redirected back to home |  |  | Pass | JB, 4/6/2020 | Pass | JY, 4/15/2020
As a player I want to be able to spectate a game so that I can watch others play checkers. | Given a pair of players is playing a game of checkers, when I choose to spectate a game then I will enter spectatr mode and view the game |  |  |  |  | Pass | JY, 4/15/2020
| Given that I am in spectate mode when I click the exit button then I should be taken to homepage. |  |  |  |  | Pass | JY, 4/15/2020
| Given that I am spectating a game when I click the flip board button then I expect to be shown the board from the opposite perspective. |  |  |  |  | Pass | JY, 4/15/2020
As a player I want to see visual enhancements so that I can play a nicer looking game of checkers | Given I am playing a game of checkers, I want my pieces to look visually enhanced |  |  |  |  | Pass | JY, 4/15/2020
| Given I am playing a game of checkers, I want the site design to bee visually enhanced |  |  |  |  | Pass | JY, 4/15/2020